## Sheet1
Task Name
Sky Sync Installation
Configure Office 365 Tenant
Provision users in Office 365
Assign licenses to users in Office 365
Provision OneDrive
Initial Assessment
Validate that there are no username collisions between migrating users and Target tenant
Document SharePoint settings in Source and Target
Document Teams settings in Source and Target
Document resources in scope for migration
Provision Required Access
Request required permissions
Register for SkySync account (Service account)
Provide Office 365 permissions (Service account)
Provide tool permissions (SkySync account) to Source and Destination
Finalize Migration Groups (Migration "waves")
Create iHub design in SPO
iHub in SPO - UAT and Bug Fixing
Configure SkySync and ShareGate
SPO / OneDrive / Teams POC
Pre-create SharePoint sites in Target tenant
Pre-create OneDrive sites in Target tenant
Pre-create Teams sites in Target tenant
Enable SharePoint site features in Target tenant
Pre-create SharePoint site structure in Target tenant
Pre-create OneDrive site structure in Target tenant
Pre-create Teams site structure in Target tenant
Migrate POC SharePoint data
Migrate POC OneDrive data
Migrate POC Teams data
Analyze SharePoint results and resolve errors
Analyze OneDrive results and resolve errors
Analyze Teams results and resolve errors
Finalize Communication Plan
Develop end user communication plan / timeline
Create end user communication template
Verify migration group CSV/Excel file
SPO / OneDrive / Teams Pre-stage for Pilot
Pre-create SharePoint sites in Target tenant for pilot
Pre-create Teams sites in Target tenant for pilot
Enable SharePoint site features in Target tenant for pilot
Pre-create SharePoint site structure in Target tenant for pilot
Pre-create OneDrive site structure in Target tenant for pilot
Pre-create Teams site structure in Target tenant for pilot
Pre-stage pilot SharePoint
Pre-stage pilot OneDrive
Pre-stage pilot Teams
Regression testing for pilot
SPO / OneDrive / Teams Full Prestage *In Waves*
Pre-create SharePoint sites in Target tenant for remaining users
Pre-create OneDrive sites in Target tenant for remaining users
Pre-create Teams sites in Target tenant for remaining users
Enable SharePoint site features in Target tenant for remaining content
Pre-create SharePoint site structure in Target tenant for remaining users
Pre-create Teams site structure in Target tenant for remaining users
Pre-stage remaining SharePoint content
Pre-stage remaining OneDrive content
Pre-stage remaining Teams content
Smoke testing for remaining users content
Pilot Migration Preparation
Send end user communication
Pilot Delta Migration
Send migration start update
Delta migration for SharePoint lists
Validate SharePoint / OneDrive Sync
Delta migration for Teams lists and Conversations
Validate Teams list and Conversation
Provide post-migration support
Cutover Go / No-Go
Document pilot issues and lessons learned
Discuss pilot results and lessons learned
Make go / no-go determination for cutover migration
Cutover Migration Preparation
Send end user communication
Google Drive to SPO / OneDrive / Teams Cutover
Send migration start update
Delta migration for SharePoint lists
Delta migration for Teams lists
Validate SharePoint Sync
Validate OneDrive Sync
Validate Teams Sync
Send mid-migration update
Google Drive /iHub Cutover
Test SPO/OneDrive/Teams content
Set google drive to read only mode
Send migration completion update
Post-Cutover Support
Provide post-migration support
**These steps are subject to change based on additional "migration approach" discovery.